## Slide 1
Release 10.9 Retrospective
RCA & Action Items — Dana, Shlomi, Rajeev squads Timeline: Sprint 0 (Sep 30) → FF (Jan 26) → CF (Feb 17) → GA (May 13)

## Slide 2
KPI Comparison: 10.8 → 10.9
Metric | KPI | 10.8 | 10.9 | Δ | Trend
Breached FF (stories) | 0 | 37 | 27 | -10 | ✅ Improved (-27%)
Breached CF (stories) | 0 | 23 | 32 | +9 | ❌ Worse (+39%)
Breached CF (bugs) | 0 | 4 | 5 | +1 | ➡️ Flat
Regression total | <10 | 50 | 95 | +45 | ❌ Worse (+90%)
Regression in hardening | <4 | 17 | 40 | +23 | ❌ Worse (+135%)
Automation detection | +20% | 32% | 12.6% | -19pp | ❌ Dropped

## Slide 3
Per-GM Breakdown
Metric | Dana 10.8→10.9 | Shlomi 10.8→10.9 | Rajeev 10.8→10.9
Breached FF | 7→4 ✅ | 0→10 ❌ | 30→13 ✅
Breached CF Stories | 6→0 ✅ | 3→6 ❌ | 14→26 ❌
Breached CF Bugs | 2→1 ✅ | 2→2 ➡️ | 0→2 ❌
Regression total | 19→54 ❌ | 4→14 ❌ | 27→27 ➡️
Regression hardening | 11→24 ❌ | 1→10 ❌ | 5→6 ➡️
Verdict | FF/CF great Regressions bad | All worse | FF great CF doubled

## Slide 4
✅ Improvements 10.8 → 10.9
FF discipline improved: 37 → 27 breaches (-27%)
Dana CF breach → zero stories at Code Freeze
Rajeev FF halved: 30 → 13
Apex regressions halved: 6 → 3
Rajeev regressions stable despite more scope
Positive pattern: upgrade testing during development (Rajeev)

## Slide 5
Root Cause Analysis

## Slide 6
Regression Total: 50 → 95 (+90%) — Top Contributors
Squad (GM) | 10.8 | 10.9 | Δ | Root Cause
Nils (Dana) | 16 | 47 | +31 | React Migration — all new bugs = regressions
GreenBoat (Rajeev) | 15 | 17 | +2 | Upgrade scenarios, EF cache, code conflicts
Driver (Shlomi) | 1 | 8 | +7 | VME/VAIO — low quality dev testing
Azure (Dana) | 3 | 6 | +3 | GPv2 performance, recovery stuck
VRA (Shlomi) | 3 | 5 | +2 | Scale issues at large setups
Apex (Rajeev) | 6 | 3 | -3 | ✅ Improved

## Slide 7
FF & CF Breach Root Causes
FF Breaches (27 total):
• Cyber Resilience (7): Late requirements — design approved end Sprint 4
• Apex Legends (7): Stories in RFT but QA bandwidth limited
• GreenBoat (4): Dependencies on Linux migration + waiver
• Nils (2): FE tweaks enabled late (same as 10.8!)
CF Breaches (32 stories):
• GreenBoat (13): Public Cloud test setup not ready
• Apex Legends (12): Testing started late, stories stuck in QA
• Cyber Resilience (4): LTS late start
• Driver (2): Urgent HF + HV stabilization

## Slide 8
Automation Detection: 32% → 12.6%
Most concerning metric — target is +20% improvement, we went backwards
Why?
• New bugs concentrated in React (Nils) and VME (Driver)
• These areas have LOW automation coverage
• React has Cypress but insufficient for complex scenarios
• VME/Driver has minimal automation — 'N/A' per Shlomi
Impact: 12 of 95 bugs found by automation (vs 16/50 in 10.8)

## Slide 9
QA-Dev Interface: Ready For Testing Backlog

## Slide 10
RFT Backlog Growth: 75 → 196 items (+161%)
Milestone | Items in RFT | Notes
10.9 Sprint 1 | 75 | Baseline
10.9 Sprint 4 | 84 | +12%
10.9 Feature Freeze | 87 | Stable
10.9 Code Freeze | 45 | Consumed during hardening
10.10 Sprint 1 | 94 | Immediately refilled
10.10 Sprint 2 | 169 | ⚠️ Spike
Today | 196 | ❌ +161% from baseline

## Slide 11
RFT Backlog: Per Squad & Aging
Current: 196 items. 75% older than 30 days. 55 items > 3 months.
Top squads:
• Nils (Dana): 50 items, avg 71 days old
• Opus (Dana): 31 items, avg 57 days old
• Azure (Dana): 25 items, avg 97 days old ⚠️
• Apex Legends (Rajeev): 16 items, avg 90 days old
• GreenBoat (Rajeev): items in queue
10.8 FF vs 10.9 FF: RFT grew from 39 → 64 items (+64%)
Stuck > 3 weeks: doubled from 3 → 7

## Slide 12
Epic & Story Lifecycle SLA Analysis

## Slide 13
Story Active Cycle Time (In Progress → Completed)
Phase | All (n=61) | Dana | Shlomi | Rajeev ⚠️
Dev Time (IP → RFT) | 27d avg / 12d med | 7d / 5d | 11d / 7d | 42d / 15d
QA Queue (RFT → Testing) | 25d avg / 14d med | 15d / 19d | 10d / 6d | 44d / 29d ⚠️
QA Execution (Testing → Done) | 15d avg / 3d med | 2d / 0d | 6d / 2d | 33d / 28d ⚠️
Total Active Cycle | 56d avg / 27d med | 18d / 11d ✅ | 24d / 21d ✅ | 90d / 74d ❌

## Slide 14
Story Lifecycle — Per Squad
Squad (GM) | Total Active (avg/med) | QA Queue (avg/med) | Concern
GreenBoat (Rajeev) | 95d / 80d | 45d / 29d | ⚠️ Longest cycle + QA queue
Apex Legends (Rajeev) | 83d / 27d | 41d / 26d | ⚠️ High variability
Cyber Resilience (Shlomi) | 24d / 24d | 11d / 6d | ✅ Healthy
Cloud Azure (Dana) | 19d / 19d | 16d / 19d | ✅ Healthy

## Slide 15
Epic Lifecycle Phases
Workflow: New → Ready For Dev → In Development → Ready To Ship
FR Phase (New → Ready For Development):
Overall: avg 71d, median 21d (n=11)
Shlomi: avg 94d — late requirement injection
Rajeev: avg 57d, median 35d
Planning Wait (Ready For Dev → In Development):
Overall: avg 43d, median 30d (n=10)
Rajeev: avg 50d — epics sit idle ~7 weeks after FR done
Shlomi: avg 26d — reasonable
Design stories (once started): avg 31d — not a bottleneck ✅

## Slide 16
Key Findings: Where Does Time Go?
1. QA Queue is #1 time sink for Rajeev
44 days avg waiting in RFT. GreenBoat=45d, Apex=41d
2. Rajeev's cycle is 4-5× longer than Dana/Shlomi
90d vs 18-24d. Long dev + long QA queue + long QA execution
3. FR Phase avg 71 days at epic level
Shlomi's epics avg 94d. Requirements not locked early enough
4. Planning idle after FR: 43 days
Epics ready for dev but nobody picks them up for 6 weeks
5. Dana & Shlomi story cycles are healthy (18-24d)

## Slide 17
10.8 Retro Cross-Reference

## Slide 18
10.8 Findings: What Was Actually Addressed?
10.8 Finding | 10.9 Result | Verdict
Don't enable FE tweaks late | Same issue, Nils 16→47 | ❌ NOT ADDRESSED
React side-by-side comparison | Not done | ❌ NOT ADDRESSED
Increase Cypress coverage | Rate dropped 32%→12.6% | ❌ NOT ADDRESSED
Clarify cross-team ownership | Same GB/AWS blame | ❌ NOT ADDRESSED
Upgrade test during dev | Rajeev regressions FLAT | ✅ ADDRESSED
Scale setups lacking | Still not ready | ❌ NOT ADDRESSED
ZIC timeline different | Under discussion | ⏳ IN PROGRESS
Enhance ZIC quality | Cyber FF breach +7 | ❌ NOT ADDRESSED

## Slide 19
10.8 → 10.9 Improvement Score
1 / 8 improvements implemented
1 / 8 in progress
6 / 8 not addressed
We must break this pattern in 10.10

## Slide 20
Action Items

## Slide 21
Dana Mittelman — Priority: REGRESSION (54 bugs)
D1: Enforce tweak activation policy
No FE tweak after Sprint 5. Dev+QA sign-off required.
Target: Zero regressions from late-activated tweaks
D2: React Migration quality gate
Side-by-side visual comparison with AngularJS before merge
Target: Nils regressions < 20 (down from 47)
D3: Cypress coverage plan for React
Top 5 high-traffic pages covered by Sprint 3
Target: Automation detection > 25% for Nils bugs
D4: Decouple Linux Migration tool from RC
Target: Linux migration regressions moved to pre-CF

## Slide 22
Shlomi Apel — Priority: ALL METRICS REGRESSED
S1: Driver squad — mandatory dev self-testing checklist
5 basic scenarios per feature before 'Ready for Testing'
Target: Driver regressions < 4 (down from 8)
S2: HV testing setup always-available policy
Target: Zero CF breaches from setup unavailability
S3: Scale testing capacity — escalate to VP/Infra
Target: Scale tests parallel to dev (not sequential)
S4: Cyber Resilience — requirements locked by Sprint 2
Target: Zero FF breaches from late requirements
S5: VRA scale checkpoint at Sprint 4
Target: VRA P1 scale regressions = 0

## Slide 23
Rajeev Srivastav — Priority: CF BREACH + QA QUEUE
R1: GreenBoat — stabilize test env BEFORE Sprint 5
If not ready by Sprint 5, descope dependent features
Target: GB CF breach < 5 (down from 13)
R2: Cross-team impact ownership contract
Signed ownership doc at design phase for cross-team changes
Target: Zero cross-team blame escalations
R3: Apex Legends — QA bandwidth reservation
Pre-allocate QA capacity in Sprint 5-6
Target: Zero FF breaches from 'ready but not tested'
R4: Upgrade regression gate in CI
Target: Upgrade regressions < 3

## Slide 24
Org-Level Actions (Sandra)
O1: Automation investment plan
Dedicated automation sprint per GM. Target: > 25% rate
O2: Tweak activation = formal release milestone
Jira workflow step by Sprint 5. Measurable.
O3: ZIC timeline decision
Same FF/CF dates or different milestones? Decide now.
O4: Mid-release regression checkpoint (Sprint 4)
If any squad > 5 regressions by Sprint 4 → remediation plan
L1: RFT WIP limit per squad (max 15 items)
Target: RFT backlog < 100 at FF (down from 196)
L5: Rajeev QA queue SLA: max 14 days in RFT
Current: 44d avg. Investigate QA capacity gap.

## Slide 25
Jira Links — Drill Down & Analyze
Dashboard & Filters:
• Dashboard: https://zerto.atlassian.net/jira/dashboards/10405
• FF Breach: https://zerto.atlassian.net/issues/?filter=21636
• CF Stories: https://zerto.atlassian.net/issues/?filter=21637
• CF Bugs: https://zerto.atlassian.net/issues/?filter=21638
Regressions per Squad (10.9):
• Nils (47): Squad - Eng - Nils + affectedVersion=10.9 + Regression=Yes
• GreenBoat (17): Squad GreenBoat + affectedVersion=10.9 + Regression=Yes
• Driver (8): Squad Driver + affectedVersion=10.9 + Regression=Yes
• Azure (6): Squad Cloud Azure + affectedVersion=10.9 + Regression=Yes
• VRA (5): Squad VRA + affectedVersion=10.9 + Regression=Yes
• Apex (3): Squad Apex Legends + affectedVersion=10.9 + Regression=Yes
All 10.9 Regressions:
• affectedVersion=10.9 AND Regression=Yes AND status not in (Obsolete)

## Slide 26
Summary & Next Steps
What went right:
FF discipline improved (-27%), Dana CF→zero, Rajeev FF halved
What went wrong:
Regressions +90%, CF +39%, Automation rate halved
6/8 improvements from 10.8 NOT addressed
Root causes:
React/Nils tweaks, QA queue bottleneck (Rajeev), late requirements
For 10.10 — non-negotiables:
1. No tweak activation after Sprint 5
2. RFT WIP limits enforced
3. Mid-release checkpoint at Sprint 4
4. QA capacity aligned to dev output (esp. Rajeev squads)